## Slide 1: Phillips Mine Fire A Containment & Extinguishment Design Plan
ASMR Big Sky Montana: June 3rd-7th, 2019
By: Buck Neely, P.E.; Tim Danehy, QEP; Ryan Mahony; Bryan Page; Margaret Dunn, P.G.; Dan Guy P.G.; Rich Beam P.G.; Dean Baker P.E.; Roger Rummel P.E.
Case Study

## Slide 2: OVERVIEW
Site History
Site Evaluation / Design Approach
  Containment
  Extinguishment
Monitoring Wells
  Temperature Buttons
  Mine-atmosphere readings
Final Design Configuration
Current Construction Progress

## Slide 3: Site History
H.C. Frick Coal and Coke Company – Phillips Mine
  Location South of Pittsburgh
    North Union Twp., Fayette Co. PA
  1907 – 1944 (Pittsburgh Coalbed)
Fire Age & Origin Uncertain
  “Barren – Coal Burned Out”
  “Burned Sec”
  1950’s and Earlier
Current Fire
  Observed & Reported to PA DEP 1997
Bureau of Abandoned Mine Reclamation (BAMR)
  Subsurface Investigations: 2003 & 2008
    Fire Extent, Potential to Migrate, Potential to Impact Man-made Structures
BioMost, Inc. – 2014 Contract
Notes: BAMR subsurface investigation performed to evaluate: Fire’s Extent, Potential to Migrate, and Potential to impact made-made structures

## Slide 4: Site Investigation
Gas Station Proximity
Vents & ‘Hoar Frost’
BAMR Wells
On-site Materials

## Slide 5: Site Investigation
Gas Station Proximity
Vents & ‘Hoar Frost’
BAMR Wells
On-site Materials

## Slide 6: Site Investigation
Gas Station Proximity
Vents & ‘Hoar Frost’
BAMR Wells
On-site Materials

## Slide 7: Site Investigation
Gas Station Proximity
Vents & ‘Hoar Frost’
BAMR Wells
On-site Materials

## Slide 8: Drill Baby Drill!
  Exploratory Bore Holes (48)
  Monitoring Wells (43)
    Mine Pool (6)
    Mine Atmosphere
    VOIDS
    Cores
  Goal = Cold Perimeter

## Slide 9: Monitoring Wells
Steel – sch40
Custom Slotted Screens
  PVC Casing 5 ft Screen Height
  Steel Casing 21 ft Screen Height
Shale Traps
Air Tight – (Capped)
Road Building

## Slide 10: Monitoring Wells
Data Collection
Temperature (°F)
  Deployable Buttons
    Highest Recorded Temp: 158 °F (#9)
Gas Composition (MSA Altair 4x Multigas Detector
  O2 – (vol %)
    Lowest: 0.9% (#13)
  H2S – (ppm)
    N/D
  CO – (ppm)
    Highest: 512 ppm (#9)
  Combined Explosives – (%LEL)
    Highest: 14% (#38)
Water Samples (as necessary)

## Slide 11: Design Concept
Safety Related Appurtenances
  Water Source Tie-in, Holding Pond, Firefighting Foam & Equipment
Water Handling
  Temporary Infiltration Structure, Diversion Ditches & Sed. Basin
Temporary Surface Seal: Smother the Vents
Northern Air Barrier (Crop)
Eastern Air Barrier / Seal (Crop)
Southern Fire Barrier (Cut-Off Trench)
Permanent Infiltration System

## Slide 12: Design Plan

## Slide 13: Safety Related Appurtenances
Holding Pond
Public Water Source Connection
Firefighting Foam & Equipment

## Slide 14: Water Handling
Diversion Ditches
Temporary Infiltration Structure
Temporary Sediment Basin

## Slide 15: Water Handling
Diversion Ditches
Temporary Infiltration Structure
Temporary Sediment Basin

## Slide 16: Water Handling
Diversion Ditches
Temporary Infiltration Structure
Temporary Sediment Basin

## Slide 17: Water Handling
Diversion Ditches
Temporary Infiltration Structure
Temporary Sediment Basin

## Slide 18: Temporary Surface Seal
Clay Thickness: 3 FT

## Slide 19: Air Barrier Details

## Slide 20: Northern Air Barrier
Old Piccolomini Strip Pit (Crop)
Aided in Restricting Oxygen

## Slide 21: Northern Air Barrier

## Slide 22: Northern Air Barrier

## Slide 23: Eastern Air Barrier / Seal
Crop Area Historically Identified as Burned

## Slide 24: Eastern Air Barrier / Seal
Red Dog & Bony Present

## Slide 25: Eastern Air Barrier / Seal

## Slide 26: Eastern Air Barrier / Seal
Air Barrier / Seal Installation

## Slide 27: Southern Fire Barrier
Cut-Off Trench

## Slide 28: Southern Fire Barrier
Cut-Off Trench w/ Fire Barrier

## Slide 29: Southern Fire Barrier
Cut-Off Trench

## Slide 30: Southern Fire Barrier
Cut-Off Trench

## Slide 31: Southern Fire Barrier
Southern Fire Barrier

## Slide 32: Permanent Infiltration System
Permanent Wet Meadow
Rock Drain Extending to Daylight

## Slide 33: Extinguishment
Mine Through the Actively Burning Areas
  Extinguish & Quench

## Slide 34: Extinguishment
Preparing to Excavate Through Hot Area
  Proceeding up-valley
~80 Degree Soil on Grade 3/20/2019

## Slide 35: Extinguishment

## Slide 36: Construction Cost Projection
Design Completed 2015
Engineers Est. Construction Cost (BioMost, Inc): $7,220,000
  ~1.5 Million CY JOB
Winning Contractor Bid: $7,197,263 – $6.9M Awarded
Earthmovers Unlimited, Inc. (Contractor)
Estimate was 0.3% Higher than Bid (~5% > Award)

## Slide 37: Construction Status
Construction Began: Spring 2017
Construction Delays
  2018 Wettest Year on Record (PIT – 57.8”)
  Average Precipitation ~38”
Current Status: All Barriers are Installed, Staging to Mine Through the Actively Burning Zones
  Extinguish & Quench as Needed

## Slide 38: Gloom & Doom - Expectations
  Construction Delays Possibly a Blessing
  So Far - Safer, Easier, Less Dramatic

## Slide 39: QUESTIONS?
-Thank You-
&
Acknowledgements
  PA DEP (BAMR)
  Earthmovers Unlimited Inc. (Contractor)
  Landowners